## Project Team
SPS120 Project Management Document
| Course Section: | NBB
| PROJECT #: | 1
| Due Date: | February:21,2022
| Group Name: | Group 7 |  | # Planned Sprints | 4
| Group Members |  | Role | Length of Each Sprint | 2 | Days
| Soni Dev |  | Fishbone Diagram; Mind mapping | * meeting after each sprint to review work
| Singh Mannav |  | Multiple Solutions; Trade Off Analysis | * send status report if you can't attend
| Tonga Yonkeu Serge |  | Implementation(Flowchart); Video Editing
| ---- |  | ------

## Project Execution
PROJECT MANAGEMENT DOCUMENT | [R] Responsible, [A] Accountable, [C] Consulted, [I] Informed
| RACI | [6 empty] | Agile
Tasks or Deliverables | SONI DEV | MANNAV SINGH | TONGA YONKEU SERGE | Student 4 | Professor | Target Sprint # | STATUS | Value Points (Marks) | Story Points (Time) | Bang for the Buck (V/SP)
PROJECT MANAGEMENT | A | R,C | I | - |  | 1 | COMPLETED | 20
Project Preparation Plan | A | R,C | I |  |  | 1 | COMPLETED | 5 | 1 | 5
Project 1 Checkpoint | A | R,C | I |  |  | 1 | COMPLETED | 5 | 1 | 5
Completed PM Spreadsheet submitted with documentation package | A | R,C | I |  |  | 1 | COMPLETED | 5 | 1 | 5
Project Management Retroperspective provides sufficient detail | A | R,C | I |  |  | 1 | COMPLETED | 5 | 1 | 5
PROBLEM SOLVING | A | R,C | I | - |  | 1 | COMPLETED | 20
Define the problem (what, where, when, who) | A | R,C | I |  |  | 1 | COMPLETED | 1 | 1 | 1
Create an Ishikawa Diagram (at least 10 causes) | A | R,C | I |  |  | 1 | COMPLETED | 2 | 3 | 0.66667
Write up explanation of causes | A | R,C | I |  |  | 1 | COMPLETED | 3 | 1 | 3
Create a Mind Map diagram (at least 20 bubbles) | A | R,C | I |  |  | 1 | COMPLETED | 1 | 2 | 0.5
Provide Multiple Solutions (at least 5) | A | R,C | I |  |  | 1 | COMPLETED | 2 | 3 | 0.66667
Write up explanation of solutions | A | R,C | I |  |  | 1 | COMPLETED | 3 | 2 | 1.5
Write up trade off analysis of your chosen 5 solutions | A | R,C | I |  |  | 1 | COMPLETED | 3
Create a flow chart to show how you will implement your solutions | A | R,C | I |  |  | 1 | COMPLETED | 2
Write up detailed explanation of flow chart | A | R,C | I |  |  | 1 | COMPLETED | 3
DOCUMENATION | A | R,C | I |  |  | 1 | COMPLETED | 20
Create a Word or PDF document with all items | A | R,C | I |  |  | 1 | COMPLETED | 2
Ensure document is properly formatted | A | R,C | I |  |  | 1 | COMPLETED | 4
Check document for clarity and concision | A | R,C | I |  |  | 1 | COMPLETED | 3
Check document for proper spelling and grammar | A | R,C | I |  |  | 1 | COMPLETED | 3
Ensure all diagrams are cleanr, clear, and professional | A | R,C | I |  |  | 1 | COMPLETED | 3
Ensure all diagrams are properly labeled | A | R,C | I |  |  | 1 | COMPLETED | 1
Ensure document cover page contains all necessary info | A | R,C | I |  |  | 1 | COMPLETED | 1
Ensure document pages are numbered | A | R,C | I |  |  | 1 | COMPLETED | 1
Ensure document is in PDF or MS Word format | A | R,C | I |  |  | 1 | COMPLETED | 1
Ensure document file name uses specified naming convention | A | R,C | I |  |  | 1 | COMPLETED | 1
PRESENTATION | A | R,C | I |  |  | 1 | COMPLETED | 20
Team member 1 created professional portion with clear AV | A | R,C | I |  |  | 1 | COMPLETED | 1.5
Team member 2 created professional portion with clear AV | A | R,C | I |  |  | 1 | COMPLETED | 1.5
Team member 3 created professional portion with clear AV | A | R,C | I |  |  | 1 | COMPLETED | 1.5
Team member 4 created professional portion with clear AV | A | R,C | I |  |  | 1 | COMPLETED | 1.5
Ensure all members introduce themselves | A | R,C | I |  |  | 1 | COMPLETED | 1
Ensure all sections are covered | A | R,C | I |  |  | 1 | COMPLETED | 5
Ensure all parts are properly memorized and delivered | A | R,C | I |  |  | 1 | COMPLETED | 3
Ensure each section includes appropriate/readable graphic | A | R,C | I |  |  | 1 | COMPLETED | 2
Create intro and outro graphics containing necessary info | A | R,C | I |  |  | 1 | COMPLETED | 1
Combine all parts to fit within time limit | A | R,C | I |  |  | 1 | COMPLETED | 2
The value in this case is the number of marks you will get.
Story Points is how much work the task will take to complete.
Bang for the Buck is the value you will receive relative to the amount of work you have to do. Calculated by dividing value by story points.
Story Points - rates the stories from smallest to largest. Assign 1 to smallest and _n_ to the largest. Choose a story that will take a full sprint to complete. Make that your biggest. If a story takes more than one sprint it needs to be split into multiple.
Validate that the story follows INVEST principals (Independent, Negotiable, Valuable, Estimable, Small, Testable)
[R] Responsible = delivers, [A] Accountable = checks for completeness and makes sure it's done on time, [C] Consulted = provides input, [I] Informed = Informed
If you have a PM then you can add (A)accountable to the RACI

## Plan and Retrospective
SPS120 Project Plan and Retrospective
Sprint 1
| Date Planned for Start | February:8,2022
| Date Planned for Finish | February:10,2022 | Tip: CTRL ; inserts today's date
| What is to be completed this sprint? | PROJECT MANAGEMENT
| Date Started | February:8,2022
| Date Finished | February:10,2022
| Did you get everything you wanted done? | YES
| How many meetings did you have? | 1
| Does everyone normally attend? | YES
| What worked -> what did we do well? | COOPERATION AMONG TEAM MEMBERS
| Notable obstacles | TIME MANAGEMENT, FLOW OF THE DISCUSSION (WE OFTEN WENT OFF TOPIC)
| What to improve for next sprint? | TIME MANAGEMENT, FLOW OF THE DISCUSSION
Sprint 2
| Date Planned for Start | February:11,2022
| Date Planned for Finish | February:13,2022
| What is to be completed this sprint? | PROBLEM SOLVING
| Date Started | February:11,2022
| Date Finished | February:13,2022
| Did you get everything you wanted done? | YES
| How many meetings did you have? | 1
| Does everyone normally attend? | YES
| What worked -> what did we do well? | COOPERATION, SUPPORT AND TIME MANAGEMENT
| Notable obstacles | FLOW OF THE DISCUSSION WENT OFF TIPIC SOMETIMES
| What to improve for next sprint? | FLOW OF THE DISCUSSION
Sprint 3
| Date Planned for Start | February:14,2022
| Date Planned for Finish | February:16,2022
| What is to be completed this sprint? | DOCUMENTATION
| Date Started | February:14,2022
| Date Finished | February:16,2022
| Did you get everything you wanted done? | YES
| How many meetings did you have? | 1
| Does everyone normally attend? | YES
| What worked -> what did we do well? | COOPERATION, TEAM SUPPORT, TIME MANAGEMENT AND ALSO THE CLARITY OF THE DISCUSSION (TOPIC)
| Notable obstacles | MANAGING THE TEAM AND THE MEMBERS
| What to improve for next sprint? | TEAM AND TIME MANAGEMENT
Sprint 4
| Date Planned for Start | February:17,2022
| Date Planned for Finish | February:19,2022
| What is to be completed this sprint? | PRESENTATION
| Date Started | February:17,2022
| Date Finished | February:19,2022
| Did you get everything you wanted done? | YES
| How many meetings did you have? | 1
| Does everyone normally attend? | YES
| What worked -> what did we do well? | COOPERATION,TIME MANAGEMENT, SUPPORT, CLARITY OF THE TOPIC
| Notable obstacles | MAYBE WE SHOULD TAKE LONGER SESSIONS FOR THE MEETING
| What to improve for next sprint? | TIME FOR THE MEETINGS SHOULD BE LONGER THAN BEFORE
Project Retroperspective (What worked well? What didn't? How can your group improve for the next project?)
WORKED WELL - COOPERATION,TIME MANAGEMENT, SUPPORT, CLARITY OF THE TOPIC
WHAT DIDN’T - TIME MANAGEMENT AND TEAM MANAGEMENT
IMPROVEMENT - MAYBE WE CAN ABLE TO SCHEDULE PRE MEETING PLANS TO AVOID THE PROBLEMS OF TIME MANAGEMENT AND FOR TEAM MANAGEMENT WE WILL CHOSE A TEAM LEADER FOR EACH
MEETINGS SO THAT FOR THAT SESSION EVERYONE WILL OFFER HIS PLANNING FOR THAT SPECIFIC SESSION IN ORDER TO MAINTAIN THE DISCIPLINE