## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Project Team
| Table 1 | Project Team
Project Execution
| Table 1 | Project Execution
Plan and Retrospective
| Table 1 | Plan and Retrospective

## Project Team
SPS120 Project Management Document
| Course Section: | NBB
| PROJECT #: | 2
| Due Date: | WEEK 9
| Group Name: | GROUP 2 |  | # Planned Sprints | 4
| Group Members |  | Role | Length of Each Sprint | 2 | Days
| SONI DEV ALPESHBHAI |  | DOCUMENTATION | * meeting after each sprint to review work
| MANNAV SINGH |  | DIAGRAMS | * send status report if you can't attend
| SERGE TONGA YONKEU |  | VIDEO EDITING
| - |  | -

## Project Execution
PROJECT MANAGEMENT DOCUMENT | [R] Responsible, [A] Accountable, [C] Consulted, [I] Informed
| RACI | [6 empty] | Agile
Tasks or Deliverables | SONI DEV ALPESHBHAI | SERGE TONGA YONKEU | MANNAV SINGH | - | Professor | Target Sprint # | Status | Value Points (Marks) | Story Points (Time) | Bang for the Buck (V/SP)
PROJECT MANAGEMENT | A | R | C |  | I | 1 |  | 20
Project Preparation Plan | A | R | C |  | I | 1 |  | 5 | 1 | 5
Project 1 Checkpoint | A | R | C |  | I | 1 |  | 5 | 1 | 5
Completed PM Spreadsheet submitted with documentation package | A | R | C |  | I | 1 |  | 5 | 1 | 5
Project Management Retroperspective provides sufficient detail | A | R | C |  | I | 1 |  | 5 | 1 | 5
PROBLEM SOLVING | A | R | C |  | I | 2 |  | 20
Define the problem (what, where, when, who) | A | R | C |  | I | 1 |  | 1 | 1 | 1
Create an Ishikawa Diagram (at least 10 causes) | A | R | C |  | I | 1 |  | 2 | 3 | 0.66667
Write up explanation of causes | A | R | C |  | I | 1 |  | 3 | 1 | 3
Create a Mind Map diagram (at least 20 bubbles) | A | R | C |  | I | 1 |  | 1 | 2 | 0.5
Provide Multiple Solutions (at least 5) | A | R | C |  | I | 1 |  | 2 | 3 | 0.66667
Write up explanation of solutions | A | R | C |  | I | 1 |  | 3 | 2 | 1.5
Write up trade off analysis of your chosen 5 solutions | A | R | C |  | I | 1 |  | 3
Create a flow chart to show how you will implement your solutions | A | R | C |  | I | 1 |  | 2
Write up detailed explanation of flow chart | A | R | C |  | I | 1 |  | 3
DOCUMENATION | A | R | C |  | I | 2 |  | 20
Create a Word or PDF document with all items | A | R | C |  | I | 1 |  | 2
Ensure document is properly formatted | A | R | C |  | I | 1 |  | 4
Check document for clarity and concision | A | R | C |  | I | 1 |  | 3
Check document for proper spelling and grammar | A | R | C |  | I | 1 |  | 3
Ensure all diagrams are cleanr, clear, and professional | A | R | C |  | I | 1 |  | 3
Ensure all diagrams are properly labeled | A | R | C |  | I | 1 |  | 1
Ensure document cover page contains all necessary info | A | R | C |  | I | 1 |  | 1
Ensure document pages are numbered | A | R | C |  | I | 1 |  | 1
Ensure document is in PDF or MS Word format | A | R | C |  | I | 1 |  | 1
Ensure document file name uses specified naming convention | A | R | C |  | I | 1 |  | 1
PRESENTATION | A | R | C |  | I | 2 |  | 20
Team member 1 created professional portion with clear AV | A | R | C |  | I | 1 |  | 1.5
Team member 2 created professional portion with clear AV | A | R | C |  | I | 1 |  | 1.5
Team member 3 created professional portion with clear AV | A | R | C |  | I | 1 |  | 1.5
Team member 4 created professional portion with clear AV | A | R | C |  | I | 1 |  | 1.5
Ensure all members introduce themselves | A | R | C |  | I | 1 |  | 1
Ensure all sections are covered | A | R | C |  | I | 1 |  | 5
Ensure all parts are properly memorized and delivered | A | R | C |  | I | 1 |  | 3
Ensure each section includes appropriate/readable graphic | A | R | C |  | I | 1 |  | 2
Create intro and outro graphics containing necessary info | A | R | C |  | I | 1 |  | 1
Combine all parts to fit within time limit | A | R | C |  | I | 1 |  | 2
The value in this case is the number of marks you will get.
Story Points is how much work the task will take to complete.
Bang for the Buck is the value you will receive relative to the amount of work you have to do. Calculated by dividing value by story points.
Story Points - rates the stories from smallest to largest. Assign 1 to smallest and _n_ to the largest. Choose a story that will take a full sprint to complete. Make that your biggest. If a story takes more than one sprint it needs to be split into multiple.
Validate that the story follows INVEST principals (Independent, Negotiable, Valuable, Estimable, Small, Testable)
[R] Responsible = delivers, [A] Accountable = checks for completeness and makes sure it's done on time, [C] Consulted = provides input, [I] Informed = Informed
If you have a PM then you can add (A)accountable to the RACI

## Plan and Retrospective
SPS120 Project Plan and Retrospective
Sprint 1
| Date Planned for Start | 2022-07-03
| Date Planned for Finish | 2022-09-03
| What is to be completed this sprint? | DOCUMENTATION
| Date Started | 2022-07-03
| Date Finished | 2022-09-03
| Did you get everything you wanted done? | YES
| How many meetings did you have? | 1
| Does everyone normally attend? | YES
| What worked -> what did we do well? | TEAMWORK; COOPERATION
| Notable obstacles | TIME MANAGEMENT
| What to improve for next sprint? | TIME MANAGEMENT; CLARITY FOR THE TOPIC
Sprint 2
| Date Planned for Start | 2022-10-03
| Date Planned for Finish | 2022-12-03
| What is to be completed this sprint? | DIAGRAMS FOR PRESENTATION
| Date Started | 2022-10-03
| Date Finished | 2022-12-03
| Did you get everything you wanted done? | YES
| How many meetings did you have? | 1
| Does everyone normally attend? | YES
| What worked -> what did we do well? | IN MAKING DIAGRAMS AND DISCUSSING THE SOLUTIONS
| Notable obstacles | CLARITY FOR THE TOPIC
| What to improve for next sprint? | CLARITY AND WIDER PICTURE OF THE PROBLEM
Sprint 3
| Date Planned for Start | 14/03/2022
| Date Planned for Finish | 16/03/2022
| What is to be completed this sprint? | VIDEO FOR THE PRESENTATION
| Date Started | 14/03/2022
| Date Finished | 16/03/2022
| Did you get everything you wanted done? | YES
| How many meetings did you have? | 1
| Does everyone normally attend? | YES
| What worked -> what did we do well? | TIME MANAGEMENT;TEAMWORK
| Notable obstacles | THERE WERE NO OBSTACLES FOUNDED.
| What to improve for next sprint? | COOPERATION
Sprint 4
| Date Planned for Start | 17/03/2022
| Date Planned for Finish | 19/03/2022
| What is to be completed this sprint? | VIDEO EDITING
| Date Started | 17/03/2022
| Date Finished | 19/03/2022
| Did you get everything you wanted done? | YES
| How many meetings did you have? | 1
| Does everyone normally attend? | YES
| What worked -> what did we do well? | DOCUMENTATION AND VIDEO DISCUSSION MANAGEMENT
| Notable obstacles | THERE WERE NO OBSTACLES FOUNDED.
| What to improve for next sprint? | A LITTLE BIT OF TIME MANAGEMENT
Project Retroperspective (What worked well? What didn't? How can your group improve for the next project?)
WHAT WORKED WELL ? - TEAMWORK; COOPERATION; TIME MANAGEMENT
NOTABLE OBSTACLES ? - THERE WERE NO NOTABLE OBSTACLES SO FAR. Everything was handled very cautiously but still a little bit of
Time management is the area where we should work more.
IMPROVEMENT - TIME MANAGEMENT - is the area where we think we should work upon.